## Gantt Chart
Modul | Tugas / Deliverable | PJ | Mulai | Selesai | W1 (24 Sep) | [6 empty] | W2 (01 Oct) | [6 empty] | W3 (08 Oct) | [6 empty] | W4 (15 Oct) | [6 empty] | W5 (22 Oct) | [6 empty] | W6 (29 Oct) | [6 empty] | W7 (05 Nov) | [6 empty] | W8 (12 Nov) | [6 empty] | W9 (19 Nov) | [6 empty] | W10 (26 Nov) | [6 empty] | W11 (03 Dec)
[5 empty] | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06
FASE 0: PERSIAPAN PROYEK
Persiapan | Finalisasi PRD & Pembagian Modul | Semua | 2026-09-24 | 2026-09-26 | bar: W1 (24 Sep) 24 to W1 (24 Sep) 26
Persiapan | Setup Repo Git, Branch Strategy & CI | Semua | 2026-09-25 | 2026-09-27 | bar: W1 (24 Sep) 25 to W1 (24 Sep) 27
Persiapan | Desain Arsitektur MVVM & Folder Structure | Semua | 2026-09-26 | 2026-09-28 | bar: W1 (24 Sep) 26 to W1 (24 Sep) 28
Persiapan | Wireframe & UI Mockup (Figma/Draw) | Semua | 2026-09-27 | 2026-10-03 | bar: W1 (24 Sep) 27 to W2 (01 Oct) 03
Persiapan | Desain ERD Database Relasional | Bayu & Habib | 2026-09-28 | 2026-10-01 | bar: W1 (24 Sep) 28 to W2 (01 Oct) 01
FASE 1: BACKEND INFRASTRUKTUR & MODUL AUTH
Backend | Setup VPS, Install Node/Laravel + DB | Bayu & Habib | 2026-10-01 | 2026-10-03 | bar: W2 (01 Oct) 01 to W2 (01 Oct) 03
Backend | Buat Skema Tabel Users & Migrasi DB | Bayu & Habib | 2026-10-02 | 2026-10-04 | bar: W2 (01 Oct) 02 to W2 (01 Oct) 04
Backend | API Endpoint: Register (hash password) | Bayu & Habib | 2026-10-03 | 2026-10-06 | bar: W2 (01 Oct) 03 to W2 (01 Oct) 06
Backend | API Endpoint: Login (JWT issue) | Bayu & Habib | 2026-10-04 | 2026-10-07 | bar: W2 (01 Oct) 04 to W2 (01 Oct) 07
Backend | API Endpoint: Logout & Token Refresh | Bayu & Habib | 2026-10-06 | 2026-10-08 | bar: W2 (01 Oct) 06 to W3 (08 Oct) 08
Backend | API: Upload Foto Profil ke VPS Storage | Bayu & Habib | 2026-10-08 | 2026-10-11 | bar: W3 (08 Oct) 08 to W3 (08 Oct) 11
Auth (Bersama) | Flutter: UI Register & Login Screen | Naufal & Fadel | 2026-10-05 | 2026-10-09 | bar: W2 (01 Oct) 05 to W3 (08 Oct) 09
Auth (Bersama) | Flutter: AuthService & JWT Storage | Racha & Naufal | 2026-10-07 | 2026-10-10 | bar: W2 (01 Oct) 07 to W3 (08 Oct) 10
Auth (Bersama) | Flutter: Profil Screen + image_picker | Fadel & Racha | 2026-10-09 | 2026-10-12 | bar: W3 (08 Oct) 09 to W3 (08 Oct) 12
Auth (Bersama) | Testing Auth End-to-End & Bug Fix | Semua | 2026-10-12 | 2026-10-14 | bar: W3 (08 Oct) 12 to W3 (08 Oct) 14
>>> MILESTONE 1 -- Fondasi Auth & Backend Siap (14 Okt) | bar: W3 (08 Oct) 14
FASE 2A: BACKEND API SEMUA MODUL (Bayu & Habib)
Backend | DB: Tabel Items/Listings + Migrasi | Bayu | 2026-10-15 | 2026-10-17 | bar: W4 (15 Oct) 15 to W4 (15 Oct) 17
Backend | API: CRUD Items/Listings | Bayu | 2026-10-17 | 2026-10-21 | bar: W4 (15 Oct) 17 to W4 (15 Oct) 21
Backend | API: Upload Multi-Foto (3 foto) | Bayu | 2026-10-20 | 2026-10-23 | bar: W4 (15 Oct) 20 to W5 (22 Oct) 23
Backend | API: Search & Filter Kategori Akademik | Bayu | 2026-10-22 | 2026-10-25 | bar: W5 (22 Oct) 22 to W5 (22 Oct) 25
Backend | DB: Tabel Safe-Meet Points + Migrasi | Habib | 2026-10-15 | 2026-10-17 | bar: W4 (15 Oct) 15 to W4 (15 Oct) 17
Backend | API: CRUD Safe-Meet Points | Habib | 2026-10-17 | 2026-10-21 | bar: W4 (15 Oct) 17 to W4 (15 Oct) 21
Backend | API: Proximity Filter (Haversine) | Habib | 2026-10-20 | 2026-10-24 | bar: W4 (15 Oct) 20 to W5 (22 Oct) 24
Backend | DB: Tabel Barter Deals + Migrasi | Habib | 2026-10-24 | 2026-10-26 | bar: W5 (22 Oct) 24 to W5 (22 Oct) 26
Backend | API: CRUD Barter Deals | Habib | 2026-10-26 | 2026-10-30 | bar: W5 (22 Oct) 26 to W6 (29 Oct) 30
Backend | API: Dual-Confirmation Logic | Habib | 2026-10-29 | 2026-11-02 | bar: W6 (29 Oct) 29 to W6 (29 Oct) 02
Backend | API: Asset Locking Engine | Habib | 2026-11-01 | 2026-11-04 | bar: W6 (29 Oct) 01 to W6 (29 Oct) 04
Backend | DB: Tabel Handover Tokens + Reviews | Bayu | 2026-10-25 | 2026-10-27 | bar: W5 (22 Oct) 25 to W5 (22 Oct) 27
Backend | API: Generate Encrypted QR Token | Bayu | 2026-10-27 | 2026-10-31 | bar: W5 (22 Oct) 27 to W6 (29 Oct) 31
Backend | API: Verify QR (Expiry 5 min) | Bayu | 2026-10-30 | 2026-11-02 | bar: W6 (29 Oct) 30 to W6 (29 Oct) 02
Backend | API: CRUD Reviews & Ratings | Bayu | 2026-11-01 | 2026-11-04 | bar: W6 (29 Oct) 01 to W6 (29 Oct) 04
Backend | DB: Tabel Social Grants & Claims | Bayu | 2026-11-04 | 2026-11-06 | bar: W6 (29 Oct) 04 to W7 (05 Nov) 06
Backend | API: CRUD Social Grants | Bayu | 2026-11-05 | 2026-11-08 | bar: W7 (05 Nov) 05 to W7 (05 Nov) 08
Backend | API: CRUD Claims + Approval Logic | Habib | 2026-11-04 | 2026-11-08 | bar: W6 (29 Oct) 04 to W7 (05 Nov) 08
Backend | API: Generate Digital Claim Pass | Habib | 2026-11-07 | 2026-11-10 | bar: W7 (05 Nov) 07 to W7 (05 Nov) 10
Backend | Backend: API Documentation & Testing | Bayu & Habib | 2026-11-09 | 2026-11-13 | bar: W7 (05 Nov) 09 to W8 (12 Nov) 13
FASE 2B: FLUTTER FRONTEND 5 MODUL (Paralel)
M1-Listing | Flutter: UI Katalog & Detail Barang | Naufal | 2026-10-15 | 2026-10-22 | bar: W4 (15 Oct) 15 to W5 (22 Oct) 22
M1-Listing | Flutter: Form Tambah/Edit Listing | Naufal | 2026-10-20 | 2026-10-25 | bar: W4 (15 Oct) 20 to W5 (22 Oct) 25
M1-Listing | Flutter: image_picker 3 Foto Multi-Angle | Naufal | 2026-10-23 | 2026-10-28 | bar: W5 (22 Oct) 23 to W5 (22 Oct) 28
M1-Listing | Flutter: ListingViewModel & API Integration | Naufal | 2026-10-26 | 2026-10-31 | bar: W5 (22 Oct) 26 to W6 (29 Oct) 31
M1-Listing | Flutter: Search Bar & Filter UI | Naufal | 2026-10-29 | 2026-11-03 | bar: W6 (29 Oct) 29 to W6 (29 Oct) 03
M1-Listing | Flutter: Status Barang (Available->Archived) | Naufal | 2026-11-01 | 2026-11-05 | bar: W6 (29 Oct) 01 to W7 (05 Nov) 05
M1-Listing | Notifikasi: Listing Stale Alert (14 hari) | Naufal | 2026-11-04 | 2026-11-08 | bar: W6 (29 Oct) 04 to W7 (05 Nov) 08
M1-Listing | Testing & Debugging Modul 1 | Naufal | 2026-11-08 | 2026-11-15 | bar: W7 (05 Nov) 08 to W8 (12 Nov) 15
M2-Geospasial | Flutter: Setup flutter_map & Tile Layer | Bayu | 2026-10-15 | 2026-10-20 | bar: W4 (15 Oct) 15 to W4 (15 Oct) 20
M2-Geospasial | Flutter: UI Peta Interaktif + Marker | Bayu | 2026-10-19 | 2026-10-25 | bar: W4 (15 Oct) 19 to W5 (22 Oct) 25
M2-Geospasial | Flutter: Integrasi geolocator (GPS) | Bayu | 2026-10-23 | 2026-10-28 | bar: W5 (22 Oct) 23 to W5 (22 Oct) 28
M2-Geospasial | Flutter: Radius Filter UI (<1km,1-3km,>3km) | Bayu | 2026-10-27 | 2026-11-01 | bar: W5 (22 Oct) 27 to W6 (29 Oct) 01
M2-Geospasial | Flutter: CRUD Safe-Meet Point Screen | Bayu | 2026-10-30 | 2026-11-05 | bar: W6 (29 Oct) 30 to W7 (05 Nov) 05
M2-Geospasial | Flutter: Jarak Presisi & Google Maps Intent | Bayu | 2026-11-03 | 2026-11-08 | bar: W6 (29 Oct) 03 to W7 (05 Nov) 08
M2-Geospasial | Notifikasi: Meeting Reminder Alert | Bayu | 2026-11-06 | 2026-11-10 | bar: W7 (05 Nov) 06 to W7 (05 Nov) 10
M2-Geospasial | Testing & Debugging Modul 2 | Bayu | 2026-11-10 | 2026-11-15 | bar: W7 (05 Nov) 10 to W8 (12 Nov) 15
M3-Barter | Flutter: UI Pengajuan Barter (Pilih Barang) | Habib | 2026-10-15 | 2026-10-22 | bar: W4 (15 Oct) 15 to W5 (22 Oct) 22
M3-Barter | Flutter: image_picker Foto Bukti Kondisi | Habib | 2026-10-21 | 2026-10-26 | bar: W4 (15 Oct) 21 to W5 (22 Oct) 26
M3-Barter | Flutter: BarterViewModel & Negosiasi UI | Habib | 2026-10-25 | 2026-11-01 | bar: W5 (22 Oct) 25 to W6 (29 Oct) 01
M3-Barter | Flutter: Tombol Dual-Confirm & Status Lock | Habib | 2026-10-30 | 2026-11-05 | bar: W6 (29 Oct) 30 to W7 (05 Nov) 05
M3-Barter | Flutter: Cash Top-Up Input & Riwayat Barter | Habib | 2026-11-03 | 2026-11-08 | bar: W6 (29 Oct) 03 to W7 (05 Nov) 08
M3-Barter | Notifikasi: Barter Proposal Alert | Habib | 2026-11-06 | 2026-11-10 | bar: W7 (05 Nov) 06 to W7 (05 Nov) 10
M3-Barter | Testing & Debugging Modul 3 | Habib | 2026-11-10 | 2026-11-15 | bar: W7 (05 Nov) 10 to W8 (12 Nov) 15
M4-Handover | Flutter: QR Code Display Screen (penjual) | Fadel | 2026-10-15 | 2026-10-22 | bar: W4 (15 Oct) 15 to W5 (22 Oct) 22
M4-Handover | Flutter: mobile_scanner QR Reader (pembeli) | Fadel | 2026-10-21 | 2026-10-28 | bar: W4 (15 Oct) 21 to W5 (22 Oct) 28
M4-Handover | Flutter: HandoverViewModel & Verification | Fadel | 2026-10-27 | 2026-11-02 | bar: W5 (22 Oct) 27 to W6 (29 Oct) 02
M4-Handover | Flutter: Digital Receipt Screen | Fadel | 2026-11-01 | 2026-11-05 | bar: W6 (29 Oct) 01 to W7 (05 Nov) 05
M4-Handover | Flutter: Rating & Review Form + List | Fadel | 2026-11-04 | 2026-11-09 | bar: W6 (29 Oct) 04 to W7 (05 Nov) 09
M4-Handover | Notifikasi: Handover Success Alert | Fadel | 2026-11-07 | 2026-11-11 | bar: W7 (05 Nov) 07 to W7 (05 Nov) 11
M4-Handover | Testing & Debugging Modul 4 | Fadel | 2026-11-11 | 2026-11-15 | bar: W7 (05 Nov) 11 to W8 (12 Nov) 15
M5-Hibah | Flutter: UI Katalog Hibah & Detail Donasi | Racha | 2026-10-15 | 2026-10-22 | bar: W4 (15 Oct) 15 to W5 (22 Oct) 22
M5-Hibah | Flutter: image_picker Foto Barang Donasi | Racha | 2026-10-21 | 2026-10-26 | bar: W4 (15 Oct) 21 to W5 (22 Oct) 26
M5-Hibah | Flutter: Form Klaim (Urgensi + Justifikasi) | Racha | 2026-10-25 | 2026-11-01 | bar: W5 (22 Oct) 25 to W6 (29 Oct) 01
M5-Hibah | Flutter: Antrean Klaim & Donatur Approval UI | Racha | 2026-10-30 | 2026-11-05 | bar: W6 (29 Oct) 30 to W7 (05 Nov) 05
M5-Hibah | Flutter: Digital Claim Pass Screen | Racha | 2026-11-04 | 2026-11-09 | bar: W6 (29 Oct) 04 to W7 (05 Nov) 09
M5-Hibah | Notifikasi: Donation Claim Approval Alert | Racha | 2026-11-07 | 2026-11-11 | bar: W7 (05 Nov) 07 to W7 (05 Nov) 11
M5-Hibah | Testing & Debugging Modul 5 | Racha | 2026-11-11 | 2026-11-15 | bar: W7 (05 Nov) 11 to W8 (12 Nov) 15
FASE 3: INTEGRASI, TESTING & FINALISASI
Integrasi | Merge Branch -> main & Resolve Conflict | Semua | 2026-11-16 | 2026-11-19 | bar: W8 (12 Nov) 16 to W9 (19 Nov) 19
Integrasi | Integrasi Routing Antar Modul | Semua | 2026-11-18 | 2026-11-22 | bar: W8 (12 Nov) 18 to W9 (19 Nov) 22
Integrasi | End-to-End Test: 5 User Flow Utama | Semua | 2026-11-20 | 2026-11-25 | bar: W9 (19 Nov) 20 to W9 (19 Nov) 25
Integrasi | UI Polish: Konsistensi Material 3 & Overflow | Semua | 2026-11-23 | 2026-11-27 | bar: W9 (19 Nov) 23 to W10 (26 Nov) 27
Integrasi | Bug Fixing Round 1 (Critical) | Semua | 2026-11-26 | 2026-11-30 | bar: W10 (26 Nov) 26 to W10 (26 Nov) 30
Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | Semua | 2026-12-01 | 2026-12-04 | bar: W10 (26 Nov) 01 to W11 (03 Dec) 04
Integrasi | Finalisasi AI Usage Log per Anggota | Semua | 2026-12-03 | 2026-12-05 | bar: W11 (03 Dec) 03 to W11 (03 Dec) 05
Integrasi | Persiapan Demo & Code Review | Semua | 2026-12-04 | 2026-12-06 | bar: W11 (03 Dec) 04 to W11 (03 Dec) 06
>>> MILESTONE 2 -- Proyek Selesai & Rilis Final (6 Des) | bar: W11 (03 Dec) 06
LEGENDA WARNA:
Persiapan (Semua)
Auth Bersama (Naufal, Fadel, Racha)
Backend (Bayu & Habib)
M1 - Naufal (Listing)
M2 - Bayu (Geospasial)
M3 - Habib (Barter)
M4 - Fadel (Handover)
M5 - Racha (Hibah)
Integrasi (Semua)
Milestone

## To-Do per Anggota
Naufal Baihaqi Z. (2411522025) -- Frontend M1-Listing
No. | Modul | Tugas / Deliverable | Mulai | Selesai | Durasi | Status
1 | Persiapan | Finalisasi PRD & Pembagian Modul | 2026-09-24 | 2026-09-26 | 3 hari | [ ] Belum
2 | Persiapan | Setup Repo Git, Branch Strategy & CI | 2026-09-25 | 2026-09-27 | 3 hari | [ ] Belum
3 | Persiapan | Desain Arsitektur MVVM & Folder Structure | 2026-09-26 | 2026-09-28 | 3 hari | [ ] Belum
4 | Persiapan | Wireframe & UI Mockup (Figma/Draw) | 2026-09-27 | 2026-10-03 | 7 hari | [ ] Belum
5 | Auth (Bersama) | Flutter: UI Register & Login Screen | 2026-10-05 | 2026-10-09 | 5 hari | [ ] Belum
6 | Auth (Bersama) | Flutter: AuthService & JWT Storage | 2026-10-07 | 2026-10-10 | 4 hari | [ ] Belum
7 | Auth (Bersama) | Testing Auth End-to-End & Bug Fix | 2026-10-12 | 2026-10-14 | 3 hari | [ ] Belum
8 | M1-Listing | Flutter: UI Katalog & Detail Barang | 2026-10-15 | 2026-10-22 | 8 hari | [ ] Belum
9 | M1-Listing | Flutter: Form Tambah/Edit Listing | 2026-10-20 | 2026-10-25 | 6 hari | [ ] Belum
10 | M1-Listing | Flutter: image_picker 3 Foto Multi-Angle | 2026-10-23 | 2026-10-28 | 6 hari | [ ] Belum
11 | M1-Listing | Flutter: ListingViewModel & API Integration | 2026-10-26 | 2026-10-31 | 6 hari | [ ] Belum
12 | M1-Listing | Flutter: Search Bar & Filter UI | 2026-10-29 | 2026-11-03 | 6 hari | [ ] Belum
13 | M1-Listing | Flutter: Status Barang (Available->Archived) | 2026-11-01 | 2026-11-05 | 5 hari | [ ] Belum
14 | M1-Listing | Notifikasi: Listing Stale Alert (14 hari) | 2026-11-04 | 2026-11-08 | 5 hari | [ ] Belum
15 | M1-Listing | Testing & Debugging Modul 1 | 2026-11-08 | 2026-11-15 | 8 hari | [ ] Belum
16 | Integrasi | Merge Branch -> main & Resolve Conflict | 2026-11-16 | 2026-11-19 | 4 hari | [ ] Belum
17 | Integrasi | Integrasi Routing Antar Modul | 2026-11-18 | 2026-11-22 | 5 hari | [ ] Belum
18 | Integrasi | End-to-End Test: 5 User Flow Utama | 2026-11-20 | 2026-11-25 | 6 hari | [ ] Belum
19 | Integrasi | UI Polish: Konsistensi Material 3 & Overflow | 2026-11-23 | 2026-11-27 | 5 hari | [ ] Belum
20 | Integrasi | Bug Fixing Round 1 (Critical) | 2026-11-26 | 2026-11-30 | 5 hari | [ ] Belum
21 | Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | 2026-12-01 | 2026-12-04 | 4 hari | [ ] Belum
22 | Integrasi | Finalisasi AI Usage Log per Anggota | 2026-12-03 | 2026-12-05 | 3 hari | [ ] Belum
23 | Integrasi | Persiapan Demo & Code Review | 2026-12-04 | 2026-12-06 | 3 hari | [ ] Belum
| Total Tugas: | 23 item
Bayu Mutawakkil (2411522023) -- Backend Lead + Frontend M2-Geospasial
No. | Modul | Tugas / Deliverable | Mulai | Selesai | Durasi | Status
1 | Persiapan | Finalisasi PRD & Pembagian Modul | 2026-09-24 | 2026-09-26 | 3 hari | [ ] Belum
2 | Persiapan | Setup Repo Git, Branch Strategy & CI | 2026-09-25 | 2026-09-27 | 3 hari | [ ] Belum
3 | Persiapan | Desain Arsitektur MVVM & Folder Structure | 2026-09-26 | 2026-09-28 | 3 hari | [ ] Belum
4 | Persiapan | Wireframe & UI Mockup (Figma/Draw) | 2026-09-27 | 2026-10-03 | 7 hari | [ ] Belum
5 | Persiapan | Desain ERD Database Relasional | 2026-09-28 | 2026-10-01 | 4 hari | [ ] Belum
6 | Backend | Setup VPS, Install Node/Laravel + DB | 2026-10-01 | 2026-10-03 | 3 hari | [ ] Belum
7 | Backend | Buat Skema Tabel Users & Migrasi DB | 2026-10-02 | 2026-10-04 | 3 hari | [ ] Belum
8 | Backend | API Endpoint: Register (hash password) | 2026-10-03 | 2026-10-06 | 4 hari | [ ] Belum
9 | Backend | API Endpoint: Login (JWT issue) | 2026-10-04 | 2026-10-07 | 4 hari | [ ] Belum
10 | Backend | API Endpoint: Logout & Token Refresh | 2026-10-06 | 2026-10-08 | 3 hari | [ ] Belum
11 | Backend | API: Upload Foto Profil ke VPS Storage | 2026-10-08 | 2026-10-11 | 4 hari | [ ] Belum
12 | Auth (Bersama) | Testing Auth End-to-End & Bug Fix | 2026-10-12 | 2026-10-14 | 3 hari | [ ] Belum
13 | Backend | DB: Tabel Items/Listings + Migrasi | 2026-10-15 | 2026-10-17 | 3 hari | [ ] Belum
14 | M2-Geospasial | Flutter: Setup flutter_map & Tile Layer | 2026-10-15 | 2026-10-20 | 6 hari | [ ] Belum
15 | Backend | API: CRUD Items/Listings | 2026-10-17 | 2026-10-21 | 5 hari | [ ] Belum
16 | M2-Geospasial | Flutter: UI Peta Interaktif + Marker | 2026-10-19 | 2026-10-25 | 7 hari | [ ] Belum
17 | Backend | API: Upload Multi-Foto (3 foto) | 2026-10-20 | 2026-10-23 | 4 hari | [ ] Belum
18 | Backend | API: Search & Filter Kategori Akademik | 2026-10-22 | 2026-10-25 | 4 hari | [ ] Belum
19 | M2-Geospasial | Flutter: Integrasi geolocator (GPS) | 2026-10-23 | 2026-10-28 | 6 hari | [ ] Belum
20 | Backend | DB: Tabel Handover Tokens + Reviews | 2026-10-25 | 2026-10-27 | 3 hari | [ ] Belum
21 | Backend | API: Generate Encrypted QR Token | 2026-10-27 | 2026-10-31 | 5 hari | [ ] Belum
22 | M2-Geospasial | Flutter: Radius Filter UI (<1km,1-3km,>3km) | 2026-10-27 | 2026-11-01 | 6 hari | [ ] Belum
23 | Backend | API: Verify QR (Expiry 5 min) | 2026-10-30 | 2026-11-02 | 4 hari | [ ] Belum
24 | M2-Geospasial | Flutter: CRUD Safe-Meet Point Screen | 2026-10-30 | 2026-11-05 | 7 hari | [ ] Belum
25 | Backend | API: CRUD Reviews & Ratings | 2026-11-01 | 2026-11-04 | 4 hari | [ ] Belum
26 | M2-Geospasial | Flutter: Jarak Presisi & Google Maps Intent | 2026-11-03 | 2026-11-08 | 6 hari | [ ] Belum
27 | Backend | DB: Tabel Social Grants & Claims | 2026-11-04 | 2026-11-06 | 3 hari | [ ] Belum
28 | Backend | API: CRUD Social Grants | 2026-11-05 | 2026-11-08 | 4 hari | [ ] Belum
29 | M2-Geospasial | Notifikasi: Meeting Reminder Alert | 2026-11-06 | 2026-11-10 | 5 hari | [ ] Belum
30 | Backend | Backend: API Documentation & Testing | 2026-11-09 | 2026-11-13 | 5 hari | [ ] Belum
31 | M2-Geospasial | Testing & Debugging Modul 2 | 2026-11-10 | 2026-11-15 | 6 hari | [ ] Belum
32 | Integrasi | Merge Branch -> main & Resolve Conflict | 2026-11-16 | 2026-11-19 | 4 hari | [ ] Belum
33 | Integrasi | Integrasi Routing Antar Modul | 2026-11-18 | 2026-11-22 | 5 hari | [ ] Belum
34 | Integrasi | End-to-End Test: 5 User Flow Utama | 2026-11-20 | 2026-11-25 | 6 hari | [ ] Belum
35 | Integrasi | UI Polish: Konsistensi Material 3 & Overflow | 2026-11-23 | 2026-11-27 | 5 hari | [ ] Belum
36 | Integrasi | Bug Fixing Round 1 (Critical) | 2026-11-26 | 2026-11-30 | 5 hari | [ ] Belum
37 | Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | 2026-12-01 | 2026-12-04 | 4 hari | [ ] Belum
38 | Integrasi | Finalisasi AI Usage Log per Anggota | 2026-12-03 | 2026-12-05 | 3 hari | [ ] Belum
39 | Integrasi | Persiapan Demo & Code Review | 2026-12-04 | 2026-12-06 | 3 hari | [ ] Belum
| Total Tugas: | 39 item
Muhammad Habib (2411522024) -- Backend Lead + Frontend M3-Barter
No. | Modul | Tugas / Deliverable | Mulai | Selesai | Durasi | Status
1 | Persiapan | Finalisasi PRD & Pembagian Modul | 2026-09-24 | 2026-09-26 | 3 hari | [ ] Belum
2 | Persiapan | Setup Repo Git, Branch Strategy & CI | 2026-09-25 | 2026-09-27 | 3 hari | [ ] Belum
3 | Persiapan | Desain Arsitektur MVVM & Folder Structure | 2026-09-26 | 2026-09-28 | 3 hari | [ ] Belum
4 | Persiapan | Wireframe & UI Mockup (Figma/Draw) | 2026-09-27 | 2026-10-03 | 7 hari | [ ] Belum
5 | Persiapan | Desain ERD Database Relasional | 2026-09-28 | 2026-10-01 | 4 hari | [ ] Belum
6 | Backend | Setup VPS, Install Node/Laravel + DB | 2026-10-01 | 2026-10-03 | 3 hari | [ ] Belum
7 | Backend | Buat Skema Tabel Users & Migrasi DB | 2026-10-02 | 2026-10-04 | 3 hari | [ ] Belum
8 | Backend | API Endpoint: Register (hash password) | 2026-10-03 | 2026-10-06 | 4 hari | [ ] Belum
9 | Backend | API Endpoint: Login (JWT issue) | 2026-10-04 | 2026-10-07 | 4 hari | [ ] Belum
10 | Backend | API Endpoint: Logout & Token Refresh | 2026-10-06 | 2026-10-08 | 3 hari | [ ] Belum
11 | Backend | API: Upload Foto Profil ke VPS Storage | 2026-10-08 | 2026-10-11 | 4 hari | [ ] Belum
12 | Auth (Bersama) | Testing Auth End-to-End & Bug Fix | 2026-10-12 | 2026-10-14 | 3 hari | [ ] Belum
13 | Backend | DB: Tabel Safe-Meet Points + Migrasi | 2026-10-15 | 2026-10-17 | 3 hari | [ ] Belum
14 | M3-Barter | Flutter: UI Pengajuan Barter (Pilih Barang) | 2026-10-15 | 2026-10-22 | 8 hari | [ ] Belum
15 | Backend | API: CRUD Safe-Meet Points | 2026-10-17 | 2026-10-21 | 5 hari | [ ] Belum
16 | Backend | API: Proximity Filter (Haversine) | 2026-10-20 | 2026-10-24 | 5 hari | [ ] Belum
17 | M3-Barter | Flutter: image_picker Foto Bukti Kondisi | 2026-10-21 | 2026-10-26 | 6 hari | [ ] Belum
18 | Backend | DB: Tabel Barter Deals + Migrasi | 2026-10-24 | 2026-10-26 | 3 hari | [ ] Belum
19 | M3-Barter | Flutter: BarterViewModel & Negosiasi UI | 2026-10-25 | 2026-11-01 | 8 hari | [ ] Belum
20 | Backend | API: CRUD Barter Deals | 2026-10-26 | 2026-10-30 | 5 hari | [ ] Belum
21 | Backend | API: Dual-Confirmation Logic | 2026-10-29 | 2026-11-02 | 5 hari | [ ] Belum
22 | M3-Barter | Flutter: Tombol Dual-Confirm & Status Lock | 2026-10-30 | 2026-11-05 | 7 hari | [ ] Belum
23 | Backend | API: Asset Locking Engine | 2026-11-01 | 2026-11-04 | 4 hari | [ ] Belum
24 | M3-Barter | Flutter: Cash Top-Up Input & Riwayat Barter | 2026-11-03 | 2026-11-08 | 6 hari | [ ] Belum
25 | Backend | API: CRUD Claims + Approval Logic | 2026-11-04 | 2026-11-08 | 5 hari | [ ] Belum
26 | M3-Barter | Notifikasi: Barter Proposal Alert | 2026-11-06 | 2026-11-10 | 5 hari | [ ] Belum
27 | Backend | API: Generate Digital Claim Pass | 2026-11-07 | 2026-11-10 | 4 hari | [ ] Belum
28 | Backend | Backend: API Documentation & Testing | 2026-11-09 | 2026-11-13 | 5 hari | [ ] Belum
29 | M3-Barter | Testing & Debugging Modul 3 | 2026-11-10 | 2026-11-15 | 6 hari | [ ] Belum
30 | Integrasi | Merge Branch -> main & Resolve Conflict | 2026-11-16 | 2026-11-19 | 4 hari | [ ] Belum
31 | Integrasi | Integrasi Routing Antar Modul | 2026-11-18 | 2026-11-22 | 5 hari | [ ] Belum
32 | Integrasi | End-to-End Test: 5 User Flow Utama | 2026-11-20 | 2026-11-25 | 6 hari | [ ] Belum
33 | Integrasi | UI Polish: Konsistensi Material 3 & Overflow | 2026-11-23 | 2026-11-27 | 5 hari | [ ] Belum
34 | Integrasi | Bug Fixing Round 1 (Critical) | 2026-11-26 | 2026-11-30 | 5 hari | [ ] Belum
35 | Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | 2026-12-01 | 2026-12-04 | 4 hari | [ ] Belum
36 | Integrasi | Finalisasi AI Usage Log per Anggota | 2026-12-03 | 2026-12-05 | 3 hari | [ ] Belum
37 | Integrasi | Persiapan Demo & Code Review | 2026-12-04 | 2026-12-06 | 3 hari | [ ] Belum
| Total Tugas: | 37 item
Fadel Muhammad (2411522029) -- Frontend M4-Handover
No. | Modul | Tugas / Deliverable | Mulai | Selesai | Durasi | Status
1 | Persiapan | Finalisasi PRD & Pembagian Modul | 2026-09-24 | 2026-09-26 | 3 hari | [ ] Belum
2 | Persiapan | Setup Repo Git, Branch Strategy & CI | 2026-09-25 | 2026-09-27 | 3 hari | [ ] Belum
3 | Persiapan | Desain Arsitektur MVVM & Folder Structure | 2026-09-26 | 2026-09-28 | 3 hari | [ ] Belum
4 | Persiapan | Wireframe & UI Mockup (Figma/Draw) | 2026-09-27 | 2026-10-03 | 7 hari | [ ] Belum
5 | Auth (Bersama) | Flutter: UI Register & Login Screen | 2026-10-05 | 2026-10-09 | 5 hari | [ ] Belum
6 | Auth (Bersama) | Flutter: Profil Screen + image_picker | 2026-10-09 | 2026-10-12 | 4 hari | [ ] Belum
7 | Auth (Bersama) | Testing Auth End-to-End & Bug Fix | 2026-10-12 | 2026-10-14 | 3 hari | [ ] Belum
8 | M4-Handover | Flutter: QR Code Display Screen (penjual) | 2026-10-15 | 2026-10-22 | 8 hari | [ ] Belum
9 | M4-Handover | Flutter: mobile_scanner QR Reader (pembeli) | 2026-10-21 | 2026-10-28 | 8 hari | [ ] Belum
10 | M4-Handover | Flutter: HandoverViewModel & Verification | 2026-10-27 | 2026-11-02 | 7 hari | [ ] Belum
11 | M4-Handover | Flutter: Digital Receipt Screen | 2026-11-01 | 2026-11-05 | 5 hari | [ ] Belum
12 | M4-Handover | Flutter: Rating & Review Form + List | 2026-11-04 | 2026-11-09 | 6 hari | [ ] Belum
13 | M4-Handover | Notifikasi: Handover Success Alert | 2026-11-07 | 2026-11-11 | 5 hari | [ ] Belum
14 | M4-Handover | Testing & Debugging Modul 4 | 2026-11-11 | 2026-11-15 | 5 hari | [ ] Belum
15 | Integrasi | Merge Branch -> main & Resolve Conflict | 2026-11-16 | 2026-11-19 | 4 hari | [ ] Belum
16 | Integrasi | Integrasi Routing Antar Modul | 2026-11-18 | 2026-11-22 | 5 hari | [ ] Belum
17 | Integrasi | End-to-End Test: 5 User Flow Utama | 2026-11-20 | 2026-11-25 | 6 hari | [ ] Belum
18 | Integrasi | UI Polish: Konsistensi Material 3 & Overflow | 2026-11-23 | 2026-11-27 | 5 hari | [ ] Belum
19 | Integrasi | Bug Fixing Round 1 (Critical) | 2026-11-26 | 2026-11-30 | 5 hari | [ ] Belum
20 | Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | 2026-12-01 | 2026-12-04 | 4 hari | [ ] Belum
21 | Integrasi | Finalisasi AI Usage Log per Anggota | 2026-12-03 | 2026-12-05 | 3 hari | [ ] Belum
22 | Integrasi | Persiapan Demo & Code Review | 2026-12-04 | 2026-12-06 | 3 hari | [ ] Belum
| Total Tugas: | 22 item
M. Racha Ardiwinata (2411522020) -- Frontend M5-Hibah
No. | Modul | Tugas / Deliverable | Mulai | Selesai | Durasi | Status
1 | Persiapan | Finalisasi PRD & Pembagian Modul | 2026-09-24 | 2026-09-26 | 3 hari | [ ] Belum
2 | Persiapan | Setup Repo Git, Branch Strategy & CI | 2026-09-25 | 2026-09-27 | 3 hari | [ ] Belum
3 | Persiapan | Desain Arsitektur MVVM & Folder Structure | 2026-09-26 | 2026-09-28 | 3 hari | [ ] Belum
4 | Persiapan | Wireframe & UI Mockup (Figma/Draw) | 2026-09-27 | 2026-10-03 | 7 hari | [ ] Belum
5 | Auth (Bersama) | Flutter: AuthService & JWT Storage | 2026-10-07 | 2026-10-10 | 4 hari | [ ] Belum
6 | Auth (Bersama) | Flutter: Profil Screen + image_picker | 2026-10-09 | 2026-10-12 | 4 hari | [ ] Belum
7 | Auth (Bersama) | Testing Auth End-to-End & Bug Fix | 2026-10-12 | 2026-10-14 | 3 hari | [ ] Belum
8 | M5-Hibah | Flutter: UI Katalog Hibah & Detail Donasi | 2026-10-15 | 2026-10-22 | 8 hari | [ ] Belum
9 | M5-Hibah | Flutter: image_picker Foto Barang Donasi | 2026-10-21 | 2026-10-26 | 6 hari | [ ] Belum
10 | M5-Hibah | Flutter: Form Klaim (Urgensi + Justifikasi) | 2026-10-25 | 2026-11-01 | 8 hari | [ ] Belum
11 | M5-Hibah | Flutter: Antrean Klaim & Donatur Approval UI | 2026-10-30 | 2026-11-05 | 7 hari | [ ] Belum
12 | M5-Hibah | Flutter: Digital Claim Pass Screen | 2026-11-04 | 2026-11-09 | 6 hari | [ ] Belum
13 | M5-Hibah | Notifikasi: Donation Claim Approval Alert | 2026-11-07 | 2026-11-11 | 5 hari | [ ] Belum
14 | M5-Hibah | Testing & Debugging Modul 5 | 2026-11-11 | 2026-11-15 | 5 hari | [ ] Belum
15 | Integrasi | Merge Branch -> main & Resolve Conflict | 2026-11-16 | 2026-11-19 | 4 hari | [ ] Belum
16 | Integrasi | Integrasi Routing Antar Modul | 2026-11-18 | 2026-11-22 | 5 hari | [ ] Belum
17 | Integrasi | End-to-End Test: 5 User Flow Utama | 2026-11-20 | 2026-11-25 | 6 hari | [ ] Belum
18 | Integrasi | UI Polish: Konsistensi Material 3 & Overflow | 2026-11-23 | 2026-11-27 | 5 hari | [ ] Belum
19 | Integrasi | Bug Fixing Round 1 (Critical) | 2026-11-26 | 2026-11-30 | 5 hari | [ ] Belum
20 | Integrasi | Bug Fixing Round 2 (Minor & Edge Cases) | 2026-12-01 | 2026-12-04 | 4 hari | [ ] Belum
21 | Integrasi | Finalisasi AI Usage Log per Anggota | 2026-12-03 | 2026-12-05 | 3 hari | [ ] Belum
22 | Integrasi | Persiapan Demo & Code Review | 2026-12-04 | 2026-12-06 | 3 hari | [ ] Belum
| Total Tugas: | 22 item

## Pembagian Peran
Anggota | NIM | Peran Utama | Modul Flutter | Backend? | Catatan
Naufal Baihaqi Z. | 2411522025 | Frontend Developer | M1: Listing & QA Fisik | Tidak | Fokus penuh Flutter M1. Membantu UI Auth di Fase 1.
Bayu Mutawakkil | 2411522023 | Backend Lead + Frontend | M2: Geospasial & Safe-Meet | Ya (Lead) | Backend API M1, M2, M4, M5. Paralel Flutter M2.
Muhammad Habib | 2411522024 | Backend Lead + Frontend | M3: Barter Non-Tunai | Ya (Lead) | Backend API M2, M3, M5. Paralel Flutter M3.
Fadel Muhammad | 2411522029 | Frontend Developer | M4: Handover & Rekam Jejak | Tidak | Fokus penuh Flutter M4. Membantu UI Auth di Fase 1.
M. Racha Ardiwinata | 2411522020 | Frontend Developer | M5: Hibah Sosial Kampus | Tidak | Fokus penuh Flutter M5. Membantu UI Auth di Fase 1.

## Ringkasan Milestone
Milestone | Target Tanggal | Kriteria Selesai (Definition of Done)
Milestone 1 | 14 Oktober 2026 | Backend VPS running (Node/Laravel + PostgreSQL/MySQL) API Auth: Register, Login (JWT), Logout berfungsi Flutter: UI Register, Login, Profil + foto kamera AuthService & JWT token tersimpan di device Wireframe/Mockup 5 modul telah disetujui tim Struktur folder MVVM (views/viewmodels/models/services) siap
Milestone 2 | 6 Desember 2026 | 5 modul fungsional lengkap (CRUD + Hardware + Notifikasi) Seluruh Backend API 5 modul terdeploy di VPS Integrasi antar modul via ID (low coupling) berjalan End-to-End test 5 user flow utama PASS UI bebas overflow pada layar 5.0-6.7 inci Zero Firebase dependency di pubspec.yaml & backend AI Usage Log setiap anggota terdokumentasi Setiap anggota siap demo & jelaskan kodenya